# Level 3 Extended Diploma in Performing & Production Arts

# Unit 12 Project Proposal

| Candidate Name | Ellie Homer |
| --- | --- |
| Candidate Number | 6016164 |
| Pathway | Events management |
| Project Title | FMP |
| Section 1: Rationale (Approx 150 Words) |  |
| I enjoyed my time working on the MET connect website as it expanded my knowledge of online marketing and the influence of social media. I want to proceed with the idea of ‘Ellie’s corner’ however I want to learn and grow from addressing the issues of it. I don’t think I was consistent enough and the quality of content I was producing wasn’t up to the standard I wanted it to be. For my next project I need to post and upload on the days I say I’m going to. Making a more realistic time plan will help me stay consistent and get the grade that I want. In the plan I'm going to make sure I have a big enough gap between production and the release date. This means if I face issues that mean I get behind on work for a week or so, I will have enough time to edit and prepare before I post. This was one of my main issues with Ellie's corner which led to work building up and becoming too stressful. |  |
| Section 2: Concept (Approx 200 Words) |  |
| Working with the musical theatre students, I want to turn Ellie’s corner into a page full of behind the scenes and interview content. My main inspiration for the interviews is youtube. Before a film is released, actors usually take part in different youtube videos with different channels to promote the film. I’m going to turn Ellie’s corner into one of these pages and create fun content to help promote the musicals. Not only will this be a different way to do interviews, it will also be a chance to show the actors personalities and find out more about them as individuals. Listed in the Harvard reference box, are different videos I have found which I am using as inspiration. Each video will have a different interviewing approach, creating variety across Ellie’s corner. I am planning to record each video in a different set however, due to COVID restrictions I don't know if this will be possible. I know I want to use the photography studios with a plain white background although I don't want to use this for all the videos as I want variety. As well as the videos I will post pictures and announcements about things going on behind the scenes. Using instagram, twitter and tiktok, I will create a BTS feed on Ellie's corner. This will be an unplanned stream of information about what the musical theatre students are up to. |  |
| Section 3: Evaluation (Approx 150 Words) |  |
| My end goal is to have Ellie’s corner up and running with all my produced content. I’m going to have a launch date 5 weeks before the deadline where I will release the first video. After this I will consistently upload every week up until the deadline. This creates my target of creating 5 videos. Throughout the 5 weeks of the website being active I will frequently post behind the scenes content, I don't have an exact aim for this however I want to be posting on this more than weekly. |  |
| Proposed Research Sources and Bibliography (Harvard Format) |  |
| Youtube.com. 2021. [online] Available at: <https://www.youtube.com/watch?v=IEr_yj-8MmM> [Accessed 9 March 2021]. Youtube.com. 2021. [online] Available at: <https://www.youtube.com/watch?v=p8XP7A7kvzM> [Accessed 9 March 2021]. Youtube.com. 2021. [online] Available at: <https://www.youtube.com/watch?v=CzaJoyxRETQ> [Accessed 9 March 2021]. Youtube.com. 2021. [online] Available at: https://www.youtube.com/watch?v=cS4pXTnITY0> [Accessed 9 March 2021]. |  |

| Project Action Plan and Timetable |  |  |  |
| --- | --- | --- | --- |
| Week | Date Week Beginning | Activity / What you are intending to do - including independent study | Resources / What you will need to do it - including access to workshops |
| 1 | 15th March | Email the teacher incharge of musical theatre and propose my idea to her Find out what the musicals are and get in touch with some students Start putting in depth research about videos that have inspired me Enquire about looking at studios | Email |
| 2 | 22nd March | Start planning video ideas in detail Go look at studios, play around with cameras/ my phone (research) | Studio Cameras Stands Lighting |
| 3 | 29th March (Easter holiday begins this week) | Propose video ideas to students Get feedback, what I could improve Book studio for videos |  |
| 4 | 19th April | Record video 1 Edit video 1 Analysis Take pictures for behind the scenes Start designing ellie’s corner layout |  |
| 5 | 26th April | Record video 2 Edit video 2 Analysis BTS Finalise how ellie's corner will look ready for launch |  |
| 6 | 3rd May | ##### Ellie’s corner launch week Video 1 uploaded Record video 3 Analysis, editing and BTS |  |
| 7 | 10th May | Video 2 uploaded Record video 4 Analysis, editing, BTS |  |
| 8 | 17th May | Video 3 uploaded |  |
| 9 | 24th May | Video 4 upload Record video 5 Analysis, editing, BTS Catch up on written work |  |
| 10 | 31st May | Video 5 upload Overall analysis of FMP Catch up on written work |  |
| 11 | 7th June deadline week | All finishing touches to the website, Make sure all work is complete. | Check everything on wix websites. |